## Sheet1
Table of Contents
Section. No | Contents | Page. No
1 | Introduction | 4
2 | Literature Review | 5
2.1 | Project Network Concepts | 5
2.2 | Project Management Foundations | 5
2.3 | Critical Path Method (CPM) | 6
2.4 | PERT and Uncertainty | 6
2.5 | Time–Cost Trade-Off and Project Crashing | 7
2.6 | Earned Value Management | 7
2.7 | Risk Management in Event and Hybrid Projects | 8
2.8 | Applied Relevance to the Conference Case | 8
3 | Probability, Scenario, and Cost–Time Analysis | 8
3.1 | Baseline Network and Schedule | 8
3.2 | Probability of Completing within 45 Days | 9
3.3 | Scenario 1 – Achieving 95% Confidence | 9
3.4 | Scenario 2 and 3 – Cost–Time Trade-Off | 9
3.5 | Scenario 4 – Accelerated Venue Booking | 10
3.6 | Scenario 5 – Additional Crashing Capacity | 10
3.7 | Comparison of Scenarios and Managerial Implications | 11
3.8 | Project Monitoring and Risk Interpretation | 12
4 | Strategic Recommendations | 12
5 | Reference List | 14
6 | Appendices | 15
A | Appendix A – Baseline Schedule | 15
B | Appendix B – Network Diagram | 15
C | Appendix C – Gantt Chart | 16
D | Appendix D – Cost–Time Trade-off | 16
E | Appendix E – Scenario Tables | 17
F | Appendix F – EVM Monitoring | 18

## Sheet2
Metric | Baseline Plan | Scenario 4
Expected Duration | 41 days | 40 days
Deadline | 45 days | 45 days
Probability of Completion | 89.9% | 93.1%
Critical Path | A–D–K–L–M–N–O | A–C–H–I–J–N–O
Venue Booking Duration | Normal | 7 days faster

## Sheet3
Project Duration (Days) | Total Project Cost ($) | Interpretation
41 | 282000 | Baseline schedule
40 | — | Intermediate crash
39 | 279800 | Cost decreases
38 | 279600 | Minimum total cost (Optimal schedule)
37 | 280400 | Cost begins increasing
36 | 281200 | Further cost increase
28 | 342600 | Minimum duration but economically inefficient

## Sheet4
Scenario | Key Adjustment | Expected Project Duration (Days) | Probability of Completion by Day 45 | Total Project Cost ($) | Critical Path
Baseline | Original schedule with no crashing | 41 | 89.9% | 282000 | A–D–K–L–M–N–O
Scenario 1 | Targeted crashing to achieve ≥95% completion confidence | 38 | 98.7% | ~280,000 | A–C–H–I–J–N–O
Scenario 2 | Time–cost trade-off analysis of crashing options | 41 → 38 | 89.9% → 98.7% | 282,000 → 279,600 | Path shifts during crashing
Scenario 3 | Maximum schedule compression to minimum duration | 28 | >99% | 342600 | Multiple paths converge
Scenario 4 | Venue booking accelerated by 7 days | 40 | 93.1% | 282000 | A–C–H–I–J–N–O
Scenario 5 | Additional crashing capacity for keynote confirmation | 38 | 98.7% | 279600 | A–C–H–I–J–N–O

## Sheet5
Task | On Critical Path? | Days Crashed | Crash Cost per Day ($) | Added Direct Cost ($) | Reason for Selection
Venue Booking & Contracting | Yes | 1 | 1200 | 1200 | Early critical activity. Reducing it shortens downstream logistics chain
Catering & Layout Planning | Yes | 1 | 1400 | 1400 | Direct dependency before volunteer and logistics preparation
Volunteer Recruitment & Training | Yes | 1 | 1600 | 1600 | Key staffing preparation task immediately before logistics
On-Site Logistics Preparation | Yes | 1 | 1800 | 1800 | Final operational preparation before conference delivery
Keynote Speaker Confirmation | Becomes critical after crash | 1 | 1400 | 1400 | Controls marketing and promotion readiness
Marketing Campaign Preparation | Yes | 1 | 1600 | 1600 | Supports promotional pipeline before event launch