## Scenario 1
Activity code | Activity description | predecessors |  | Activity code | optimistic | Most likely | Pessimistic | t(e) | variance | Critical Path
1 (A) | Initial Project Kick-Off | - |  | 1 | 1 | 2 | 3 | 2 | 0.11111 | ✓ | 0 |  | 2 | 2 |  | 8 | 8 |  | 13 | 13 |  | 22
2 (B) | Define Conference Themes & Tracks | 1 |  | 2 | 4 | 6 | 10 | 6 | 1 |  | 0 | A | 0 | 4 | B | 4 | 4 | F | 4 | 4 | G | 4 | [9 empty] | 35 |  | 36
3 (C ) | Keynote Speaker Identification | 1 |  | 3 | 3 | 6 | 12 | 6 | 2.25 |  | 0 | 2 | 2 | 6 | 6 | 12 | 12 | 5 | 17 | 17 | 9 | 26 | [9 empty] | 0 | N | 0
4 (D) | Venue Booking & Contracting | 1 |  | 4 | 5 | 8 | 14 | 8 | 2.25 | ✓ | [21 empty] | 35 | 1 | 36
5 (E ) | Hybrid Technical Setup | 4 |  | 5 | 6 | 10 | 16 | 10 | 2.7778 |  |  |  |  | 2 |  | 8 |  |  |  | 8 |  | 15 | 15 |  | 22 | 22 |  | 34 | 26 |  | 35
6 (F) | Sponsorship Package Development | 2 |  | 6 | 3 | 5 | 9 | 5 | 1 |  |  |  |  | 1 | C | 1 |  |  |  | 1 | H | 1 | 1 | I | 1 | 1 | J | 1 | 0 | M | 0
7 (G) | Sponsor Outreach & Negotiation | 6 |  | 7 | 5 | 9 | 18 | 9 | 4.6944 |  |  |  |  | 3 | 6 | 9 |  |  |  | 9 | 7 | 16 | 16 | 7 | 23 | 23 | 12 | 35 | 26 | 9 | 35
8 (H) | Keynote Speaker Confirmation | 3 |  | 8 | 4 | 7 | 13 | 7 | 2.25 | [22 empty] | 36 |  | 41
9 (I) | Marketing Plan Development | 2, 8 |  | 9 | 4 | 7 | 11 | 7 | 1.3611 |  |  |  |  | 2 |  | 10 | 10 |  | 20 | [6 empty] | 10 |  | 19 | 19 |  | 26 | 0 | O | 0
10( J) | Promotional Campaign Execution | 9 |  | 10 | 7 | 12 | 20 | 12 | 4.6944 |  |  |  |  | 0 | D | 0 | 6 | E | 6 | [6 empty] | 0 | K | 0 | 0 | L | 0 | 36 | 5 | 41
11 (K) | Catering & Layout Planning | 4 |  | 11 | 6 | 9 | 14 | 9 | 1.7778 | ✓ |  |  |  | 2 | 8 | 10 | 16 | 10 | 26 | [6 empty] | 10 | 9 | 19 | 19 | 7 | 26
12 (L) | Volunteer Recruitment & Training | 11 |  | 12 | 4 | 7 | 13 | 7 | 2.25 | ✓
13 (M) | On-Site Logistics Preparation | 5, 7, 12 |  | 13 | 5 | 9 | 15 | 9 | 2.7778 | ✓
14 (N) | Conference Delivery Day | 13, 10 |  | 14 | 1 | 1 | 1 | 1 | 0 | ✓
15 (O) | Post-Event Feedback & Reporting | 14 |  | 15 | 3 | 5 | 8 | 5 | 0.69444 | ✓
[6 empty] | Mean | Probability
[6 empty] | 44 | 62.49%
Activity Code | critical activities | tc(e) | variance |  |  | 43 | 73.79%
1 | Initial Project Kick-Off | 2 | 0.11111 |  |  | 42 | 83.03%
4 | Venue Booking & Contracting | 8 | 2.25 |  |  | 41 | 89.86%
11 | Catering & Layout Planning | 9 | 1.7778 |  |  | 40 | 94.43%
12 | Volunteer Recruitment & Training | 7 | 2.25 |  |  | 39 | 97.2%
13 | On-Site Logistics Preparation | 9 | 2.7778 |  |  | 38 | 98.71%
14 | Conference Delivery Day | 1 | 0 |  |  | 36 | 99.79%
15 | Post-Event Feedback & Reporting | 5 | 0.69444
| SUM | 41 | 9.8611
Expected project duration | 41
project standard deviation | 3.1402
[5 empty] | SCHEDULED PROJECT DURATION |  |  |  | 45
chance of this project | 89.86%
chance | 95%
Project Average duration must be | 39

## Scenario 2 & 3 Crashing
| 0 |  | 2 |  | 2 |  | 8 |  | 8 |  | 12 |  | 12 |  | 19
| 0 | A | 0 |  | 1 | B | 1 |  | 1 | F | 1 |  | 1 | G | 1 | [13 empty] | 26 |  | 27
| 0 | 2 | 2 |  | 3 | 6 | 9 |  | 9 | 4 | 13 |  | 13 | 7 | 20 | [13 empty] | 0 | N | 0
[29 empty] | 26 | 1 | 27
[5 empty] | 2 |  | 6 | [5 empty] | 6 |  | 11 |  | 11 |  | 17 |  | 17 |  | 26 |  | 19 |  | 25
[5 empty] | 0 | C | 0 | [5 empty] | 0 | H | 0 |  | 0 | I | 0 |  | 0 | J | 0 |  | 1 | M | 1
[5 empty] | 2 | 4 | 6 | [5 empty] | 6 | 5 | 11 |  | 11 | 6 | 17 |  | 17 | 9 | 26 |  | 20 | 6 | 26
[29 empty] | 27 |  | 31
[5 empty] | 2 |  | 7 |  | 7 |  | 17 | [9 empty] | 7 |  | 14 |  | 14 |  | 19 |  | 0 | O | 0
[5 empty] | 1 | D | 1 |  | 3 | E | 3 | [9 empty] | 1 | K | 1 |  | 1 | L | 1 |  | 27 | 4 | 31
[5 empty] | 3 | 5 | 8 |  | 10 | 10 | 20 | [9 empty] | 8 | 7 | 15 |  | 15 | 5 | 20
[23 empty] | Indirect Cost is |  | 90000 | with | 4200 | reduction for one time unit shorten
[23 empty] | Activity ID | Slope ($) | Max crash time |  |  |  | Direct Cost
[29 empty] | Normal |  | Crash
[29 empty] | Time | Cost | Time | Cost
[23 empty] | A | - | 0 |  |  |  | 2 | 3000 | 0 | 0
[23 empty] | B | 4000 | 2 |  |  |  | 6 | 8000 | 2 | 4000
[23 empty] | C | 5000 | 2 | 1 | 0 |  | 6 | 10000 | 2 | 5000
[23 empty] | D | 6000 | 3 | 2 | 1 | 0 | 8 | 18000 | 3 | 6000
[23 empty] | E | 7000 | 3 |  |  |  | 10 | 22000 | 3 | 7000
[23 empty] | F | 3000 | 1 | 0 |  |  | 5 | 6000 | 1 | 3000
[23 empty] | G | 4000 | 3 | 2 | 1 |  | 9 | 12000 | 3 | 4000
[23 empty] | H | 6000 | 2 | 1 | 0 |  | 7 | 14000 | 2 | 6000
[23 empty] | I | 4000 | 1 | 0 |  |  | 7 | 9000 | 1 | 4000
[23 empty] | J | 5000 | 3 | 2 | 1 | 0 | 12 | 15000 | 3 | 5000
[23 empty] | K | 4000 | 2 | 1 | 0 |  | 9 | 11000 | 2 | 4000
[23 empty] | L | 3500 | 2 | 1 | 0 |  | 7 | 8000 | 2 | 3500
[23 empty] | M | 6000 | 3 | 2 | 1 | 0 | 9 | 20000 | 3 | 6000
[23 empty] | N | - | 0 |  |  |  | 1 | 30000 | 0 | 0
[23 empty] | O | 2000 | 1 | 0 |  |  | 5 | 6000 | 1 | 2000
Path duration
Paths/Iteration |  |  |  | I0 |  | I1 |  | I2 |  | I3 |  | I4 |  | I5 |  | I6 |  | I7 |  | I8 |  | I9 |  | I10
ABFGMNO |  |  |  | 37 |  | 37 |  | 37 |  | 37 |  | 37 |  | 35 |  | 34 |  | 33 |  | 33 |  | 32 |  | 30
ABIJNO |  |  |  | 33 |  | 33 |  | 32 |  | 31 |  | 30 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 28
ACHIJNO |  |  |  | 40 |  | 40 |  | 39 |  | 38 |  | 37 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 31
ADEMNO |  |  |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 34 |  | 33 |  | 32 |  | 31 |  | 30 |  | 28
ADKLMNO |  |  |  | 41 |  | 40 |  | 39 |  | 38 |  | 37 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 30
[23 empty] | Project duration | Crashed activities | Crash cost | direct cost | Indirect cost | Total cost
[22 empty] | I0 | 41 | - | - | 192000 | 90000 | 282000
[22 empty] | I1 | 40 | L | 3500 | 195500 | 85800 | 281300
[22 empty] | I2 | 39 | I, L | 7500 | 203000 | 81600 | 284600
[22 empty] | I3 | 38 | J, K | 9000 | 212000 | 77400 | 289400
[22 empty] | I4 | 37 | J, K | 9000 | 221000 | 73200 | 294200
[22 empty] | I5 | 36 | F, J, M | 14000 | 235000 | 69000 | 304000
[22 empty] | I6 | 35 | C, M | 11000 | 246000 | 64800 | 310800
[22 empty] | I7 | 34 | C, M | 11000 | 257000 | 60600 | 317600
[22 empty] | I8 | 33 | H, D | 12000 | 269000 | 56400 | 325400
[22 empty] | I9 | 32 | G, H, D | 16000 | 285000 | 52200 | 337200
[22 empty] | I10 | 31 | G, O, D | 12000 | 297000 | 48000 | 345000

## Exercise 2
Time in Workdays
# | Task Name | Optimistic Dur. | Most Likely Dur. | Pessimistic Dur. | Immediate Predecessor | Critical Path | T(e) | variance
1 | AET DATA CENTER MIGRATION | 54 | 68 | 92 |  |  | 69.6667 | 40.1111 | Expected project duration | 69 | 2.4152
2 | Team meeting | 0.5 | 1 | 1.5 |  | ✓ | 1 | 0.027778 | project standard deviation | 2.42 |  | 1. Based on these estimates and the resultant expected project duration of 69 days, the executive committee wants to know what is the probability of completing the project before a scheduled time (TS) of 68 days?
3 | Hire contractors | 6 | 7 | 8 | 2 |  | 7 | 0.11111
4 | Network design | 12 | 14 | 16 | 2 |  | 14 | 0.44444 | Scheduled duration | 68
5 | Ventilation system | — | — | — | — |  | — | —
6 | Order ventilation system | 18 | 21 | 30 | 2 |  | 22 | 4 | chance of this project | 33.97%
7 | Install ventilation system | 5 | 7 | 9 | 6 |  | 7 | 0.44444
8 | New racks | — | — | — | — |  | — | —
9 | Order new racks | 13 | 14 | 21 | 2 | ✓ | 15 | 1.7778 | 93 percent chance of completion within 68 days.
10 | Install racks | 17 | 21 | 25 | 9 | ✓ | 21 | 1.7778
11 | Power supplies and cables | — | — | — | — |  | — | — | Probablity | 93%
12 | Order power supplies & cables | 6 | 7 | 8 | 2 |  | 7 | 0.11111 | Scheduled duration | 68
13 | Install power supplies | 5 | 5 | 11 | 12, 16 |  | 6 | 1 |  |  |  | 2. The significance of this project has the executive committee very concerned. The committee has decided that more analysis of the duration of each activity is needed. Prior to conducting that effort, they asked Brian to calculate what the expected project duration would have to be to ensure a 93 percent chance of completion within 68 days.
14 | Install cables | 6 | 8 | 10 | 12, 16 | ✓ | 8 | 0.44444 | Expected project duration | Probablity
15 | Renovation of data centre | 19 | 20 | 27 | 3, 4 |  | 21 | 1.7778 | 68 | 50%
16 | City inspection | 1 | 2 | 3 | 3, 7, 10 | ✓ | 2 | 0.11111 | 67 | 66.03%
17 | Switchover Meetings | — | — | — | — |  | — | — | 66 | 79.57%
18 | Facilities | 7 | 8 | 9 | 14 |  | 8 | 0.11111 | 65 | 89.25%
19 | Operations/systems | 5 | 7 | 9 | 14 |  | 7 | 0.44444 | 64 | 95.08%
20 | Operations/telecommunications | 6 | 7 | 8 | 14 |  | 7 | 0.11111 | 63 | 98.06%
21 | Systems & applications | 7 | 7 | 13 | 14 | ✓ | 8 | 1 | 62 | 99.34%
22 | Customer service | 5 | 6 | 13 | 14 |  | 7 | 1.7778 | 61 | 99.81%
23 | Power check | 0.5 | 1 | 1.5 | 13, 14, 15 |  | 1 | 0.027778
24 | Install test servers | 5 | 7 | 9 | 2, 3, 18, 19, 20, 21 | ✓ | 7 | 0.44444
25 | Management safety check | 1 | 2 | 3 | 7, 23, 24 | ✓ | 2 | 0.11111
26 | Primary systems check | 1.5 | 2 | 2.5 | 25 | ✓ | 2 | 0.027778
27 | Set date for move | 1 | 1 | 1 | 26 | ✓ | 1 | 0
28 | Complete move | 1 | 2 | 3 | 27 | ✓ | 2 | 0.11111

## Scenario 4
Activity code | Activity description | predecessors |  | Activity code | optimistic | Most likely | Pessimistic | t(e) | variance | Critical Path
1 (A) | Initial Project Kick-Off | - |  | 1 | 1 | 2 | 3 | 2 | 0.11111 | ✓ | 0 |  | 2 | 2 |  | 8 | 8 |  | 13 | 13 |  | 22
2 (B) | Define Conference Themes & Tracks | 1 |  | 2 | 4 | 6 | 10 | 6 | 1 |  | 0 | A | 0 | 3 | B | 3 | 3 | F | 3 | 3 | G | 3 | [9 empty] | 34 |  | 35
3 (C ) | Keynote Speaker Identification | 1 |  | 3 | 3 | 6 | 12 | 6 | 2.25 | ✓ | 0 | 2 | 2 | 5 | 6 | 11 | 11 | 5 | 16 | 16 | 9 | 25 | [9 empty] | 0 | N | 0
4 (D) | Venue Booking & Contracting | 1 |  | 4 | 0 | 1 | 2 | 1 | 0.11111 | [22 empty] | 34 | 1 | 35
5 (E ) | Hybrid Technical Setup | 4 |  | 5 | 6 | 10 | 16 | 10 | 2.7778 |  |  |  |  | 2 |  | 8 |  |  |  | 8 |  | 15 | 15 |  | 22 | 22 |  | 34 | 22 |  | 31
6 (F) | Sponsorship Package Development | 2 |  | 6 | 3 | 5 | 9 | 5 | 1 |  |  |  |  | 0 | C | 0 |  |  |  | 0 | H | 0 | 0 | I | 0 | 0 | J | 0 | 3 | M | 3
7 (G) | Sponsor Outreach & Negotiation | 6 |  | 7 | 5 | 9 | 18 | 9 | 4.6944 |  |  |  |  | 2 | 6 | 8 |  |  |  | 8 | 7 | 15 | 15 | 7 | 22 | 22 | 12 | 34 | 25 | 9 | 34
8 (H) | Keynote Speaker Confirmation | 3 |  | 8 | 4 | 7 | 13 | 7 | 2.25 | ✓ | [21 empty] | 35 |  | 40
9 (I) | Marketing Plan Development | 2, 8 |  | 9 | 4 | 7 | 11 | 7 | 1.3611 | ✓ |  |  |  | 2 |  | 3 | 3 |  | 13 | [6 empty] | 3 |  | 12 | 12 |  | 19 | 0 | O | 0
10( J) | Promotional Campaign Execution | 9 |  | 10 | 7 | 12 | 20 | 12 | 4.6944 | ✓ |  |  |  | 6 | D | 6 | 12 | E | 12 | [6 empty] | 6 | K | 6 | 6 | L | 6 | 35 | 5 | 40
11 (K) | Catering & Layout Planning | 4 |  | 11 | 6 | 9 | 14 | 9 | 1.7778 |  |  |  |  | 8 | 1 | 9 | 15 | 10 | 25 | [6 empty] | 9 | 9 | 18 | 18 | 7 | 25
12 (L) | Volunteer Recruitment & Training | 11 |  | 12 | 4 | 7 | 13 | 7 | 2.25
13 (M) | On-Site Logistics Preparation | 5, 7, 12 |  | 13 | 5 | 9 | 15 | 9 | 2.7778
14 (N) | Conference Delivery Day | 13, 10 |  | 14 | 1 | 1 | 1 | 1 | 0 | ✓
15 (O) | Post-Event Feedback & Reporting | 14 |  | 15 | 3 | 5 | 8 | 5 | 0.69444 | ✓
[6 empty] | Mean | Probability
[6 empty] | 44 | 61.66%
Activity Code | critical activities | tc(e) | variance |  |  | 43 | 72.35%
1 | Initial Project Kick-Off | 2 | 0.11111 |  |  | 42 | 81.33%
3 | Keynote Speaker Identification | 6 | 2.25 |  |  | 41 | 88.23%
8 | Keynote Speaker Confirmation | 7 | 2.25 |  |  | 40 | 93.1%
9 | Marketing Plan Development | 7 | 1.3611 |  |  | 39 | 96.25%
10 | Promotional Campaign Execution | 12 | 4.6944 |  |  | 38 | 98.11%
14 | Conference Delivery Day | 1 | 0 |  |  | 36 | 99.62%
15 | Post-Event Feedback & Reporting | 5 | 0.69444
| SUM | 40 | 11.3611
Expected project duration | 40
project standard deviation | 3.3706
[5 empty] | SCHEDULED PROJECT DURATION |  |  |  | 45
chance of this project | 93.1%
chance | 95%
Project Average duration must be | 39

## Scenario 4 Crashing (2)
| 0 |  | 2 |  | 2 |  | 7 |  | 7 |  | 11 |  | 11 |  | 17
| 0 | A | 0 |  | 1 | B | 1 |  | 1 | F | 1 |  | 1 | G | 1 | [13 empty] | 26 |  | 27
| 0 | 2 | 2 |  | 3 | 5 | 8 |  | 8 | 4 | 12 |  | 12 | 6 | 18 | [13 empty] | 0 | N | 0
[29 empty] | 26 | 1 | 27
[5 empty] | 2 |  | 6 | [5 empty] | 6 |  | 11 |  | 11 |  | 17 |  | 17 |  | 26 |  | 17 |  | 25
[5 empty] | 0 | C | 0 | [5 empty] | 0 | H | 0 |  | 0 | I | 0 |  | 0 | J | 0 |  | 1 | M | 1
[5 empty] | 2 | 4 | 6 | [5 empty] | 6 | 5 | 11 |  | 11 | 6 | 17 |  | 17 | 9 | 26 |  | 18 | 8 | 26
[29 empty] | 27 |  | 31
[5 empty] | 2 |  | 3 |  | 3 |  | 13 | [9 empty] | 3 |  | 11 |  | 11 |  | 16 |  | 0 | O | 0
[5 empty] | 2 | D | 2 |  | 5 | E | 5 | [9 empty] | 2 | K | 2 |  | 2 | L | 2 |  | 27 | 4 | 31
[5 empty] | 4 | 1 | 5 |  | 8 | 10 | 18 | [9 empty] | 5 | 8 | 13 |  | 13 | 5 | 18
[23 empty] | Indirect Cost is |  | 90000 | with | 4200 | reduction for one time unit shorten
[23 empty] | Activity ID | Slope ($) | Max crash time |  |  |  | Direct Cost
[29 empty] | Normal |  | Crash
[29 empty] | Time | Cost | Time | Cost
[23 empty] | A | - | 0 |  |  |  | t(e) | 3000 | 0 | 0
[23 empty] | B | 4000 | 2 | 1 |  |  | 2 | 8000 | 2 | 4000
[23 empty] | C | 5000 | 2 | 1 | 0 |  | 6 | 10000 | 2 | 5000
[23 empty] | D | 6000 | 0 |  |  |  | 6 | 18000 | 3 | 6000
[23 empty] | E | 7000 | 3 |  |  |  | 8 | 22000 | 3 | 7000
[23 empty] | F | 3000 | 1 | 0 |  |  | 10 | 6000 | 1 | 3000
[23 empty] | G | 4000 | 3 | 2 | 1 | 0 | 5 | 12000 | 3 | 4000
[23 empty] | H | 6000 | 2 | 1 | 0 |  | 9 | 14000 | 2 | 6000
[23 empty] | I | 4000 | 1 | 0 |  |  | 7 | 9000 | 1 | 4000
[23 empty] | J | 5000 | 3 | 2 | 1 | 0 | 7 | 15000 | 3 | 5000
[23 empty] | K | 4000 | 2 | 1 |  |  | 12 | 11000 | 2 | 4000
[23 empty] | L | 3500 | 2 | 1 | 0 |  | 9 | 8000 | 2 | 3500
[23 empty] | M | 6000 | 3 | 2 |  |  | 7 | 20000 | 3 | 6000
[23 empty] | N | - | 0 |  |  |  | 9 | 30000 | 0 | 0
[23 empty] | O | 2000 | 1 | 0 |  |  | 1 | 6000 | 1 | 2000
Path duration
Paths/Iteration |  |  |  | I0 |  | I1 |  | I2 |  | I3 |  | I4 |  | I5 |  | I6 |  | I7 |  | I8 |  | I9
ABFGMNO |  |  |  | 37 |  | 37 |  | 37 |  | 37 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 30
ABIJNO |  |  |  | 33 |  | 32 |  | 31 |  | 30 |  | 29 |  | 29 |  | 29 |  | 29 |  | 28 |  | 27
ACHIJNO |  |  |  | 40 |  | 39 |  | 38 |  | 37 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 31
ADEMNO |  |  |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 26
ADKLMNO |  |  |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 33 |  | 32 |  | 29
[23 empty] | Project duration | Crashed activities | Crash cost | direct cost | Indirect cost | Total cost
[22 empty] | I0 | 40 | - | - | 192000 | 90000 | 282000
[22 empty] | I1 | 39 | I | 4000 | 196000 | 85800 | 281800
[22 empty] | I2 | 38 | J | 5000 | 201000 | 81600 | 282600
[22 empty] | I3 | 37 | J | 5000 | 206000 | 77400 | 283400
[22 empty] | I4 | 36 | F, J | 8000 | 214000 | 73200 | 287200
[22 empty] | I5 | 35 | G, C | 9000 | 223000 | 69000 | 292000
[22 empty] | I6 | 34 | G, C | 9000 | 232000 | 64800 | 296800
[22 empty] | I7 | 33 | G, H, L | 13500 | 245500 | 60600 | 306100
[22 empty] | I8 | 32 | B, H, L | 13500 | 259000 | 56400 | 315400
[22 empty] | I9 | 31 | M, O, K | 12000 | 271000 | 52200 | 323200

## Scenario 5
Activity code | Activity description | predecessors |  | Activity code | optimistic | Most likely | Pessimistic | t(e) | variance | Critical Path
1 (A) | Initial Project Kick-Off | - |  | 1 | 1 | 2 | 3 | 2 | 0.11111 | ✓ | 0 |  | 2 | 2 |  | 8 | 8 |  | 13 | 13 |  | 22
2 (B) | Define Conference Themes & Tracks | 1 |  | 2 | 4 | 6 | 10 | 6 | 1 |  | 0 | A | 0 | 3 | B | 3 | 3 | F | 3 | 3 | G | 3 | [9 empty] | 34 |  | 35
3 (C ) | Keynote Speaker Identification | 1 |  | 3 | 3 | 6 | 12 | 6 | 2.25 | ✓ | 0 | 2 | 2 | 5 | 6 | 11 | 11 | 5 | 16 | 16 | 9 | 25 | [9 empty] | 0 | N | 0
4 (D) | Venue Booking & Contracting | 1 |  | 4 | 0 | 1 | 2 | 1 | 0.11111 | [22 empty] | 34 | 1 | 35
5 (E ) | Hybrid Technical Setup | 4 |  | 5 | 6 | 10 | 16 | 10 | 2.7778 |  |  |  |  | 2 |  | 8 |  |  |  | 8 |  | 15 | 15 |  | 22 | 22 |  | 34 | 22 |  | 31
6 (F) | Sponsorship Package Development | 2 |  | 6 | 3 | 5 | 9 | 5 | 1 |  |  |  |  | 0 | C | 0 |  |  |  | 0 | H | 0 | 0 | I | 0 | 0 | J | 0 | 3 | M | 3
7 (G) | Sponsor Outreach & Negotiation | 6 |  | 7 | 5 | 9 | 18 | 9 | 4.6944 |  |  |  |  | 2 | 6 | 8 |  |  |  | 8 | 7 | 15 | 15 | 7 | 22 | 22 | 12 | 34 | 25 | 9 | 34
8 (H) | Keynote Speaker Confirmation | 3 |  | 8 | 4 | 7 | 13 | 7 | 2.25 | ✓ | [21 empty] | 35 |  | 40
9 (I) | Marketing Plan Development | 2, 8 |  | 9 | 4 | 7 | 11 | 7 | 1.3611 | ✓ |  |  |  | 2 |  | 3 | 3 |  | 13 | [6 empty] | 3 |  | 12 | 12 |  | 19 | 0 | 15 | 0
10( J) | Promotional Campaign Execution | 9 |  | 10 | 7 | 12 | 20 | 12 | 4.6944 | ✓ |  |  |  | 6 | D | 6 | 12 | E | 12 | [6 empty] | 6 | K | 6 | 6 | L | 6 | 35 | 5 | 40
11 (K) | Catering & Layout Planning | 4 |  | 11 | 6 | 9 | 14 | 9 | 1.7778 |  |  |  |  | 8 | 1 | 9 | 15 | 10 | 25 | [6 empty] | 9 | 9 | 18 | 18 | 7 | 25
12 (L) | Volunteer Recruitment & Training | 11 |  | 12 | 4 | 7 | 13 | 7 | 2.25
13 (M) | On-Site Logistics Preparation | 5, 7, 12 |  | 13 | 5 | 9 | 15 | 9 | 2.7778
14 (N) | Conference Delivery Day | 13, 10 |  | 14 | 1 | 1 | 1 | 1 | 0 | ✓
15 (O) | Post-Event Feedback & Reporting | 14 |  | 15 | 3 | 5 | 8 | 5 | 0.69444 | ✓
[6 empty] | Mean | Probability
[6 empty] | 44 | 61.66%
Activity Code | critical activities | tc(e) | variance |  |  | 43 | 72.35%
1 | Initial Project Kick-Off | 2 | 0.11111 |  |  | 42 | 81.33%
3 | Keynote Speaker Identification | 6 | 2.25 |  |  | 41 | 88.23%
8 | Keynote Speaker Confirmation | 7 | 2.25 |  |  | 40 | 93.1%
9 | Marketing Plan Development | 7 | 1.3611 |  |  | 39 | 96.25%
10 | Promotional Campaign Execution | 12 | 4.6944 |  |  | 38 | 98.11%
14 | Conference Delivery Day | 1 | 0 |  |  | 36 | 99.62%
15 | Post-Event Feedback & Reporting | 5 | 0.69444
| SUM | 40 | 11.3611
Expected project duration | 40
project standard deviation | 3.3706
[5 empty] | SCHEDULED PROJECT DURATION |  |  |  | 45
chance of this project | 93.1%
chance | 95%
Project Average duration must be | 39

## Scenario 5 Crashing
| 0 |  | 2 |  | 2 |  | 6 |  | 6 |  | 10 |  | 10 |  | 16
| 0 | A | 0 |  | 1 | B | 1 |  | 1 | F | 1 |  | 1 | G | 1 | [13 empty] | 23 |  | 24
| 0 | 2 | 2 |  | 3 | 4 | 7 |  | 7 | 4 | 11 |  | 11 | 6 | 17 | [13 empty] | 0 | N | 0
[29 empty] | 23 | 1 | 24
[5 empty] | 2 |  | 6 | [5 empty] | 6 |  | 8 |  | 8 |  | 14 |  | 14 |  | 23 |  | 16 |  | 22
[5 empty] | 0 | C | 0 | [5 empty] | 0 | H | 0 |  | 0 | I | 0 |  | 0 | J | 0 |  | 1 | M | 1
[5 empty] | 2 | 4 | 6 | [5 empty] | 6 | 2 | 8 |  | 8 | 6 | 14 |  | 14 | 9 | 23 |  | 17 | 6 | 23
[29 empty] | 24 |  | 28
[5 empty] | 2 |  | 3 |  | 3 |  | 13 | [9 empty] | 3 |  | 10 |  | 10 |  | 15 |  | 0 | O | 0
[5 empty] | 2 | D | 2 |  | 4 | E | 4 | [9 empty] | 2 | K | 2 |  | 2 | L | 2 |  | 24 | 4 | 28
[5 empty] | 4 | 1 | 5 |  | 7 | 10 | 17 | [9 empty] | 5 | 7 | 12 |  | 12 | 5 | 17
[23 empty] | Indirect Cost is |  | 90000 | with | 4200 | reduction for one time unit shorten
[23 empty] | Activity ID | Slope ($) | Max crash time | [5 empty] | Direct Cost
[31 empty] | Normal |  | Crash
[31 empty] | Time | Cost | Time | Cost
[23 empty] | A | - | 0 | [5 empty] | t(e) | 3000 | 0 | 0
[23 empty] | B | 4000 | 2 | 1 | 0 |  |  |  | 2 | 8000 | 2 | 4000
[23 empty] | C | 5000 | 2 | 1 | 0 |  |  |  | 6 | 10000 | 2 | 5000
[23 empty] | D | 6000 | 0 | [5 empty] | 6 | 18000 | 3 | 6000
[23 empty] | E | 7000 | 3 | [5 empty] | 8 | 22000 | 3 | 7000
[23 empty] | F | 3000 | 1 | 0 |  |  |  |  | 10 | 6000 | 1 | 3000
[23 empty] | G | 4000 | 3 | 2 | 1 | 0 |  |  | 5 | 12000 | 3 | 4000
[23 empty] | H | 6000 | 5 | 4 | 3 | 2 | 1 | 0 | 9 | 14000 | 2 | 6000
[23 empty] | I | 4000 | 1 | 0 |  |  |  |  | 7 | 9000 | 1 | 4000
[23 empty] | J | 5000 | 3 | 2 | 1 | 0 |  |  | 7 | 15000 | 3 | 5000
[23 empty] | K | 4000 | 2 | 1 | 0 |  |  |  | 12 | 11000 | 2 | 4000
[23 empty] | L | 3500 | 2 | 1 | 0 |  |  |  | 9 | 8000 | 2 | 3500
[23 empty] | M | 6000 | 3 | 2 | 1 | 0 |  |  | 7 | 20000 | 3 | 6000
[23 empty] | N | - | 0 | [5 empty] | 9 | 30000 | 0 | 0
[23 empty] | O | 2000 | 1 | 0 |  |  |  |  | 1 | 6000 | 1 | 2000
Path duration
Paths/Iteration |  |  |  | I0 |  | I1 |  | I2 |  | I3 |  | I4 |  | I5 |  | I6 |  | I7 |  | I8 |  | I9 |  | I10 |  | I11 |  | I12 |  | I13
ABFGMNO |  |  |  | 37 |  | 36 |  | 36 |  | 36 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 31 |  | 30 |  | 29 |  | 28 |  | 27
ABIJNO |  |  |  | 33 |  | 32 |  | 31 |  | 30 |  | 29 |  | 28 |  | 28 |  | 28 |  | 28 |  | 27 |  | 26 |  | 26 |  | 26 |  | 26
ACHIJNO |  |  |  | 40 |  | 39 |  | 38 |  | 37 |  | 36 |  | 35 |  | 34 |  | 33 |  | 32 |  | 31 |  | 30 |  | 29 |  | 28 |  | 28
ADEMNO |  |  |  | 28 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 26 |  | 25 |  | 24
ADKLMNO |  |  |  | 34 |  | 33 |  | 33 |  | 33 |  | 33 |  | 33 |  | 33 |  | 33 |  | 32 |  | 31 |  | 30 |  | 28 |  | 27 |  | 26
[23 empty] | Project duration | Crashed activities | Crash cost | direct cost | Indirect cost | Total cost
[22 empty] | I0 | 40 | - | - | 192000 | 90000 | 282000
[22 empty] | I1 | 39 | O | 2000 | 194000 | 85800 | 279800
[22 empty] | I2 | 38 | I | 4000 | 198000 | 81600 | 279600
[22 empty] | I3 | 37 | J | 5000 | 203000 | 77400 | 280400
[22 empty] | I4 | 36 | J | 5000 | 208000 | 73200 | 281200
[22 empty] | I5 | 35 | F, J | 8000 | 216000 | 69000 | 285000
[22 empty] | I6 | 34 | G, C | 9000 | 225000 | 64800 | 289800
[22 empty] | I7 | 33 | G, C | 9000 | 234000 | 60600 | 294600
[22 empty] | I8 | 32 | G, H, L | 13500 | 247500 | 56400 | 303900
[22 empty] | I9 | 31 | B, H, L | 13500 | 261000 | 52200 | 313200
[22 empty] | I10 | 30 | B, H, K | 14000 | 275000 | 48000 | 323000
[22 empty] | I11 | 29 | M, H, K | 16000 | 291000 | 43800 | 334800
[22 empty] | I12 | 28 | M, H | 12000 | 303000 | 39600 | 342600
[22 empty] | I13 | 28 | M | 6000 | 309000 | 35400 | 344400