## Template
[14 empty] | BAC (baseline total budget) | 25920 | [25 empty] | Resource cost | 40/hr
[12 empty] | Schedule information | [6 empty] | Baseline budget labor cost (in hundred $) | [21 empty] | One day | 8 hours | ---> | 8*40= | 320
|  |  | 2 | B | 4 | 4 | E | 8 |  |  |  | Activity | Duration | ES | LF | SL | Head Count | Total PV $ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  |  | 3 |  |  | 3 | [5 empty] | A | 1 | 0 | 1 | 0 | 5 | 1600 | Baseline budget labor cost (in hundred $) 1: 16 | Time periods | EV | AC | PV
|  |  | 5 | 2 | 7 | 7 | 4 | 11 |  |  |  | B | 3 | 1 | 4 | 0 | 5 | 4800 | Baseline budget labor cost (in hundred $) 2: 16; Baseline budget labor cost (in hundred $) 3: 16; Baseline budget labor cost (in hundred $) 4: 16 | 0 | 0 | 0 | 0
[12 empty] | C | 2 | 4 | 6 | 0 | 2 | 1280 | Baseline budget labor cost (in hundred $) 5: 6.4; Baseline budget labor cost (in hundred $) 6: 6.4 | 1 | 1440 | 1500 | 1600
0 | A | 2 | 2 | C | 8 |  |  |  | 11 | G | 13 | D | 3 | 6 | 9 | 0 | 2 | 1920 | Baseline budget labor cost (in hundred $) 7: 6.4; Baseline budget labor cost (in hundred $) 8: 6.4; Baseline budget labor cost (in hundred $) 9: 6.4 | 2 | 2560 | 2550 | 3200
0 |  |  | 3 | [5 empty] | 0 |  |  | E | 2 | 6 | 8 | 1 | 2 | 1280 | Baseline budget labor cost (in hundred $) 7: 6.4; Baseline budget labor cost (in hundred $) 8: 6.4 | 3 | 4240 | 4150 | 4800
0 | 2 | 2 | 5 | 6 | 11 |  |  |  | 11 | 2 | 13 | F | 1 | 9 | 10 | 0 | 5 | 1600 | Baseline budget labor cost (in hundred $) 10: 16 | 4 | 6400 | 6200 | 6400
[12 empty] | G | 2 | 10 | 12 | 0 | 2 | 1280 | Baseline budget labor cost (in hundred $) 11: 6.4; Baseline budget labor cost (in hundred $) 12: 6.4 | 5 | 6848 | 6700 | 7040
[12 empty] | H | 3 | 12 | 15 | 0 | 3 | 2880 | Baseline budget labor cost (in hundred $) 13: 9.6; Baseline budget labor cost (in hundred $) 14: 9.6; Baseline budget labor cost (in hundred $) 15: 9.6 | 6 | 7680 | 7400 | 7680
[12 empty] | I | 1 | 15 | 16 | 2 | 0 | 0 | Baseline budget labor cost (in hundred $) 16: 0 | 7
[12 empty] | J | 2 | 15 | 17 | 0 | 5 | 3200 | Baseline budget labor cost (in hundred $) 17: 16; Baseline budget labor cost (in hundred $) 18: 16 | 8
[12 empty] | K | 1 | 17 | 18 | 0 | 0 | 0 | Baseline budget labor cost (in hundred $) 18: 0 | 9
[12 empty] | L | 4 | 10 | 14 | 4 | 2 | 2560 | Baseline budget labor cost (in hundred $) 11: 6.4; Baseline budget labor cost (in hundred $) 12: 6.4; Baseline budget labor cost (in hundred $) 13: 6.4; Baseline budget labor cost (in hundred $) 14: 6.4 | 10
[12 empty] | M | 3 | 18 | 21 | 0 | 2 | 1920 | Baseline budget labor cost (in hundred $) 19: 6.4; Baseline budget labor cost (in hundred $) 20: 6.4; Baseline budget labor cost (in hundred $) 21: 6.4 | 11
[12 empty] | N | 1 | 21 | 22 | 0 | 5 | 1600 | Baseline budget labor cost (in hundred $) 22: 16 | 12
[12 empty] | O | 0 | - | - | - | 0 | 0 | [22 empty] | 13
14
|  |  | 2 | D | 7 | 7 | F | 11 |  |  |  | Total PV $ by period | [6 empty] | 1600 | 1600 | 1600 | 1600 | 640 | 640 | 1280 | 1280 | 640 | 1600 | 1280 | 1280 | 1600 | 1600 | 960 | 0 | 1600 | 1600 | 640 | 640 | 640 | 1600 | 15
|  |  | 0 |  |  | 0 |  |  | ES | ID | EF | Cumulative PV $ by period | [6 empty] | 1600 | 3200 | 4800 | 6400 | 7040 | 7680 | 8960 | 10240 | 10880 | 12480 | 13760 | 15040 | 16640 | 18240 | 19200 | 19200 | 20800 | 22400 | 23040 | 23680 | 24320 | 25920 | 16
|  |  | 2 | 5 | 7 | 7 | 4 | 11 | SL | [31 empty] | 17
[9 empty] | LS | DUR | LF | Status report ending period 1 | [6 empty] | Baseline budget labor cost (in hundred $) 3: Status report ending period 4 | 18
[12 empty] | Task | % complete | EV= % complete *total PV | AC | PV (to date) |  | CV=EV-AC | Baseline budget labor cost (in hundred $) 1: SV= EV-PV(to date); Baseline budget labor cost (in hundred $) 3: Task; Baseline budget labor cost (in hundred $) 4: % complete; Baseline budget labor cost (in hundred $) 5: EV; Baseline budget labor cost (in hundred $) 6: AC; Baseline budget labor cost (in hundred $) 7: PV; Baseline budget labor cost (in hundred $) 8: CV; Baseline budget labor cost (in hundred $) 9: SV | 19
[12 empty] | A | 90% | 1440 | 1500 | 1600 |  | -60 | Baseline budget labor cost (in hundred $) 1: -160; Baseline budget labor cost (in hundred $) 3: A; Baseline budget labor cost (in hundred $) 4: 100%; Baseline budget labor cost (in hundred $) 5: 1600; Baseline budget labor cost (in hundred $) 6: 1650; Baseline budget labor cost (in hundred $) 7: 1600; Baseline budget labor cost (in hundred $) 8: -50; Baseline budget labor cost (in hundred $) 9: 0 | 20
[12 empty] | Cumulative totals |  | 1440 | 1500 | 1600 |  | -60 | Baseline budget labor cost (in hundred $) 1: -160; Baseline budget labor cost (in hundred $) 3: B; Baseline budget labor cost (in hundred $) 4: 100%; Baseline budget labor cost (in hundred $) 5: 4800; Baseline budget labor cost (in hundred $) 6: 4550; Baseline budget labor cost (in hundred $) 7: 4800; Baseline budget labor cost (in hundred $) 8: 250; Baseline budget labor cost (in hundred $) 9: 0 | 21
22 | bar: Baseline budget labor cost (in hundred $) 3
Status report ending period 2 | bar: Baseline budget labor cost (in hundred $) 3
[12 empty] | Task | % complete | EV | AC | PV |  | CV | Baseline budget labor cost (in hundred $) 1: SV; Baseline budget labor cost (in hundred $) 3: Cumulative totals; Baseline budget labor cost (in hundred $) 5: 6400; Baseline budget labor cost (in hundred $) 6: 6200; Baseline budget labor cost (in hundred $) 7: 6400; Baseline budget labor cost (in hundred $) 8: 200; Baseline budget labor cost (in hundred $) 9: 0
[12 empty] | A | 100% | 1600 | 1650 | 1600 |  | -50 | Baseline budget labor cost (in hundred $) 1: 0
[12 empty] | B | 20% | 960 | 900 | 1600 |  | 60 | Baseline budget labor cost (in hundred $) 1: -640; Baseline budget labor cost (in hundred $) 3: Status report ending period 5 |  | EV/AC | EV/pv
[12 empty] | Cumulative totals |  | 2560 | 2550 | 3200 |  | 10 | Baseline budget labor cost (in hundred $) 1: -640; Baseline budget labor cost (in hundred $) 3: Task; Baseline budget labor cost (in hundred $) 4: % complete; Baseline budget labor cost (in hundred $) 5: EV; Baseline budget labor cost (in hundred $) 6: AC; Baseline budget labor cost (in hundred $) 7: PV; Baseline budget labor cost (in hundred $) 8: CV; Baseline budget labor cost (in hundred $) 9: SV | Time periods | CPI | SPI | Target
[12 empty] | Status report ending period 3 | [6 empty] | Baseline budget labor cost (in hundred $) 3: A; Baseline budget labor cost (in hundred $) 4: 100%; Baseline budget labor cost (in hundred $) 5: 1600; Baseline budget labor cost (in hundred $) 6: 1650; Baseline budget labor cost (in hundred $) 7: 1600; Baseline budget labor cost (in hundred $) 8: -50; Baseline budget labor cost (in hundred $) 9: 0 | 1 | 0.96 | 0.9 | 1
[12 empty] | Task | % complete | EV | AC | PV |  | CV | Baseline budget labor cost (in hundred $) 1: SV; Baseline budget labor cost (in hundred $) 3: B; Baseline budget labor cost (in hundred $) 4: 100%; Baseline budget labor cost (in hundred $) 5: 4800; Baseline budget labor cost (in hundred $) 6: 4550; Baseline budget labor cost (in hundred $) 7: 4800; Baseline budget labor cost (in hundred $) 8: 250; Baseline budget labor cost (in hundred $) 9: 0 | 2 | 1.0039 | 0.8 | 1
[12 empty] | A | 100% | 1600 | 1650 | 1600 |  | -50 | Baseline budget labor cost (in hundred $) 1: 0; Baseline budget labor cost (in hundred $) 3: C; Baseline budget labor cost (in hundred $) 4: 35%; Baseline budget labor cost (in hundred $) 5: 448; Baseline budget labor cost (in hundred $) 6: 500; Baseline budget labor cost (in hundred $) 7: 640; Baseline budget labor cost (in hundred $) 8: -52; Baseline budget labor cost (in hundred $) 9: -192 | 3 | 1.0217 | 0.88333 | 1
[12 empty] | B | 55% | 2640 | 2500 | 3200 |  | 140 | Baseline budget labor cost (in hundred $) 1: -560; Baseline budget labor cost (in hundred $) 3: D | 4 | 1.0323 | 1 | 1
[41 empty] | 5 | 1.0221 | 0.97273 | 1 | bar: Baseline budget labor cost (in hundred $) 3
[19 empty] | Baseline budget labor cost (in hundred $) 3: Cumulative totals; Baseline budget labor cost (in hundred $) 5: 6848; Baseline budget labor cost (in hundred $) 6: 6700; Baseline budget labor cost (in hundred $) 7: 7040; Baseline budget labor cost (in hundred $) 8: 148; Baseline budget labor cost (in hundred $) 9: -192 | 6 | 1.0378 | 1 | 1
[12 empty] | Cumulative totals |  | 4240 | 4150 | 4800 |  | 90 | Baseline budget labor cost (in hundred $) 1: -560
Status report ending period 6
[21 empty] | Task | % complete | EV | AC | PV | CV | SV
[21 empty] | A | 100% | 1600 | 1650 | 1600 | -50 | 0
[21 empty] | B | 100% | 4800 | 4550 | 4800 | 250 | 0
[12 empty] | At the end of period 6 the project is behind schedule and under cost. | [6 empty] | Baseline budget labor cost (in hundred $) 3: C; Baseline budget labor cost (in hundred $) 4: 100%; Baseline budget labor cost (in hundred $) 5: 1280; Baseline budget labor cost (in hundred $) 6: 1200; Baseline budget labor cost (in hundred $) 7: 1280; Baseline budget labor cost (in hundred $) 8: 80; Baseline budget labor cost (in hundred $) 9: 0
D
E
[21 empty] | Cumulative totals |  | 7680 | 7400 | 7680 | 280 | 0

## Sheet2
Period | PV | EV | AC | Cum PV | Cum EV | Cum AC | SV | CV | SPI | CPI
1 | 1600 | 1500 | 1600 | 1600 | 1500 | 1600 | -100 | -100 | 0.94 | 0.94
2 | 1600 | 1500 | 1650 | 3200 | 3000 | 3250 | -200 | -250 | 0.94 | 0.92
3 | 1600 | 1400 | 1600 | 4800 | 4400 | 4850 | -400 | -450 | 0.92 | 0.91
4 | 1600 | 1500 | 1650 | 6400 | 5900 | 6500 | -500 | -600 | 0.92 | 0.91
5 | 640 | 650 | 700 | 7040 | 6550 | 7200 | -490 | -650 | 0.93 | 0.91
6 | 640 | 700 | 750 | 7680 | 7250 | 7950 | -430 | -700 | 0.94 | 0.91
7 | 1280 | 1300 | 1350 | 8960 | 8550 | 9300 | -410 | -750 | 0.95 | 0.92
8 | 1280 | 1400 | 1400 | 10240 | 9950 | 10700 | -290 | -750 | 0.97 | 0.93
9 | 640 | 700 | 680 | 10880 | 10650 | 11380 | -230 | -730 | 0.98 | 0.94
10 | 1600 | 1700 | 1600 | 12480 | 12350 | 12980 | -130 | -630 | 0.99 | 0.95
11 | 1280 | 1400 | 1300 | 13760 | 13750 | 14280 | -10 | -530 | 1 | 0.96
12 | 1280 | 1300 | 1200 | 15040 | 15050 | 15480 | 10 | -430 | 1 | 0.97
13 | 1600 | 1600 | 1500 | 16640 | 16650 | 16980 | 10 | -330 | 1 | 0.98
14 | 1600 | 1600 | 1550 | 18240 | 18250 | 18530 | 10 | -280 | 1 | 0.99
15 | 960 | 960 | 950 | 19200 | 19210 | 19480 | 10 | -270 | 1 | 0.99
16 | 0 | 0 | 0 | 19200 | 19210 | 19480 | 10 | -270 | 1 | 0.99
17 | 1600 | 1600 | 1600 | 20800 | 20810 | 21080 | 10 | -270 | 1 | 0.99
Figure X. Earned Value performance showing the relationship between Planned Value (PV), Earned Value (EV), and Actual Cost (AC) over six reporting periods.
Figure Y. Schedule Performance Index (SPI) and Cost Performance Index (CPI) illustrating schedule recovery and cost efficiency during the project lifecycle.
The cost–schedule graph compares Planned Value (PV), Earned Value (EV), and Actual Cost (AC) over the first six reporting periods. The results show that the project experienced a slow start during the early stages, with EV falling below PV, indicating that progress was initially behind schedule. However, corrective actions enabled the team to recover schedule performance by Period 4, where EV converged with PV. The index graph further confirms this pattern, with SPI initially below 1 before returning to approximately 1 by Period 6. At the same time, CPI remained above 1 in most periods, indicating that the project maintained cost efficiency and remained under budget. Overall, the monitoring results suggest that the project team successfully addressed early delays and delivered the project on time while controlling costs effectively.

## Sheet1
Task | Duration | ES | LF = ES + Dur
Initial Team Meeting | 1 | 0 | 1
Understand Case | 3 | 1 | 4
Build Baseline | 2 | 4 | 6
Scenario 1–3 | 3 | 6 | 9 | Task | Duration | Headcount | Total PV ($)
Scenario 4–5 | 2 | 6 | 8 | 2 | 1 | 5 | 1×5×320 = 1,600
Midpoint Review | 1 | 9 | 10 | 3 | 3 | 5 | 3×5×320 = 4,800
Plan Presentation | 2 | 10 | 12 | 4 | 2 | 2 | 2×2×320 = 1,280
Create Slides | 3 | 12 | 15 | 5 | 3 | 2 | 3×2×320 = 1,920
Buffer | 1 | 15 | 16 | 6 | 2 | 2 | 2×2×320 = 1,280
Practice | 2 | 15 | 17 | 7 | 1 | 5 | 1×5×320 = 1,600
Presentation | 1 | 17 | 18 | 8 | 2 | 2 | 2×2×320 = 1,280
Write Report | 4 | 10 | 14 | 9 | 3 | 3 | 3×3×320 = 2,880
Integration | 3 | 18 | 21 | 10 | 1 | 0 | 0
Final Review | 1 | 21 | 22 | 11 | 2 | 5 | 2×5×320 = 3,200
Submission | 0 | 21 | 21 | 12 | 1 | 0 | 0
|  |  |  | 13 | 4 | 2 | 4×2×320 = 2,560
|  |  |  | 14 | 3 | 2 | 3×2×320 = 1,920
|  |  |  | 15 | 1 | 5 | 1×5×320 = 1,600
|  |  |  | 16 | 0 | 0 | 0